## Excel2LaTeX (hidden)
RangeAddress | Options | CellWidth | Indent | FileName

## Sheet1
Year | Semester | Task |  | Milestone
1 | 1st | Train power model development | Computational simulation of traction power transformer
Computational simulation of train power system
|  | RTS energy model development | Train model integration with real case-study
| 2nd |  | Computational simulation of railway power system
Algorithm implementation in a compatible language
|  | Energy measurement system: node development | Hardware development of energy measurement node
2 | 1st |  | Results acquistion: testbed validation of energy measurement node | Publication: energy measurement node
|  | RTS wireless smart metering network model development | Computational simulation of RTS wireless smart metering network
RTS wireless smart metering network integration with real case-study
| 2nd |  | System integration with energy measurement nodes | Publication: RTS wireless smart metering network
|  | System integration | Development of energy data storage system;
System integration with RTS wireless smart metering network
3 | 1st |  | Results acquistion: RTS wireless smart metering system | Publication: RTS wireless smart metering system
|  | Thesis Delivery | Document writing
2nd
Thesis Delivery
|  |  | Public Presentation | Public Presentation